SPRINTPLAN

Resource Allocation Engine

First-Time Setup Guide · Windows

## What Is This App?

SprintPlan is a browser-based resource planning tool for Trading and C&S delivery teams. It calculates how many developers are needed per sprint based on epic story points, analysis due dates, and team velocity — accounting for Canadian bank holidays and business days only.

It runs entirely on your local machine. No data leaves your computer.

## What You Need

| 1 | Node.js (LTS) The JavaScript runtime that powers the app. Download once, used forever. |
| --- | --- |
| 2 | The app file sprint-planner.jsx — the single file containing the entire application. |
| 3 | A terminal Command Prompt or PowerShell — already on your Windows machine. |

## Step-by-Step Setup

### Step 1 — Install Node.js

- Open your browser and go to: nodejs.org

- Click the large green LTS button to download the installer (.msi file)

- Run the downloaded file and click "Next" through all the steps — leave all defaults as-is

- When it finishes, click Close

| ⚠️ | Download the .msi installer, NOT the zip file. The installer sets everything up automatically. The zip requires manual configuration. |
| --- | --- |

Verify the install worked — open Command Prompt and run:

node -v

You should see a version number like  v22.x.x . If you get an error, restart your computer and try again.

### Step 2 — Create the Project Folder

Open Command Prompt (press Win + R, type cmd, press Enter) and run these commands one at a time:

npm create vite@latest sprint-planner -- --template react

When prompted, press Enter to confirm. Then:

cd sprint-planner

npm install

This creates the project structure and downloads all dependencies. It takes about a minute.

### Step 3 — Add the App File

- Navigate to the sprint-planner folder you just created

- Open the src subfolder

- You will see a file called App.jsx — delete it or replace it

- Copy the sprint-planner.jsx file you received into this folder

- Rename it to App.jsx

| 💡 | The file must be named exactly App.jsx (capital A, lowercase jsx) and must be inside the src folder. |
| --- | --- |

### Step 4 — Run the App

In Command Prompt, make sure you are in the sprint-planner folder, then run:

npm run dev

You will see output ending in something like  Local: http://localhost:5173/ . Open that address in your browser.

| ✓ | The app is running. You can now use it in your browser. Keep the Command Prompt window open — closing it stops the app. |
| --- | --- |

## Every Time After (30 Seconds)

Once set up, starting the app takes three steps:

cd sprint-planner

npm run dev

Then open http://localhost:5173 in your browser.

## How to Use the App

### Epic Input Tab

This is your starting point. You can either:

- Type epics in manually — click + Add Row and fill in Epic Name, SP, and Analysis Due date

- Paste directly from Excel — copy your rows (Name, SP, Analysis Due columns) and paste anywhere on the table

The app calculates two dates automatically as you type:

- Solo Build Date — how long this epic would take if one developer started immediately after analysis, ignoring all other work. Reference only.

- Planned Build Date — the real scheduled completion date, accounting for team capacity, other epics running in parallel, and sprint availability.

### Team Velocity (Sidebar)

Paste your team data from Excel into the Team Velocity box. Set the velocity column number (0 = column A, 3 = column D). The app shows detected team size and average daily velocity.

### Sprint Config (Sidebar)

- Start sprint # — the sprint number label for the first sprint (e.g. 90)

- # sprints — how many sprints to plan ahead

- Total devs pool — the total number of developers available

- Sprint 1 start — the calendar date your first sprint begins

### Output Tabs

- Demand Table — sprint-by-sprint view of devs needed, devs free, and utilisation

- Utilisation Chart — bar chart with a capacity line showing where you are over or under

- Epic Breakdown — click any sprint to see exactly which epics are active and how many devs each is consuming

- Gantt — horizontal timeline showing each epic across sprints

## How Dates Are Calculated

The planned build date is derived using this logic:

| Step | Detail |
| --- | --- |
| Per-dev daily velocity | Average of all team members' daily velocity figures |
| Dev-days needed | SP ÷ per-dev daily velocity |
| First eligible sprint | First sprint whose end date is after the analysis due date |
| Greedy packing | Epic consumes dev-days from each sprint in order, using as many devs as needed, up to the total pool |
| Build complete | Last business day of the final sprint segment assigned to the epic |
| Business days | Monday to Friday only, excluding Canadian federal bank holidays |

## Troubleshooting

| Problem | Fix |
| --- | --- |
| 'node' is not recognised | Restart Command Prompt after installing Node.js. If still failing, restart your computer. |
| Port 5173 already in use | Another app is using that port. Vite will automatically try 5174, 5175, etc. — check the terminal output for the actual URL. |
| App shows blank page | Check the terminal for errors. Most likely the App.jsx file is not in the src folder or is named incorrectly. |
| Overflow warning on epics | Increase the # sprints value in the sidebar until the warning clears. |
| Dates look wrong | Check your Analysis Due date format — it must be YYYY-MM-DD (e.g. 2026-03-15). |
| Pasting from Excel doesn't work | Make sure you are pasting into the table area of the Epic Input tab, not into an individual cell. |

## Quick Reference

| Column A in Excel | Index 0 |
| --- | --- |
| Column D in Excel | Index 3 |
| Column J in Excel | Index 9 |
| Column K in Excel | Index 10 |
| Sprint length | 14 calendar days |
| Business days | Mon–Fri, CA bank holidays excluded |
| App URL | http://localhost:5173 |
| Stop the app | Press Ctrl + C in Command Prompt |

SprintPlan · Trading & C&S Resource Allocation · Runs locally · No data leaves your machine